## Sheet1
S.NO | Module | Handover | Document Locations / Script locations | status | Pending with | Automation Tool
1 | Oracle Data Integrator | Pruthvi Raj | Path: K:\BDTS-MW-Documents$\EIDIKOPITEAM\Handover\Noola Srinivas Handover\ODI | KT | NA | NA
2 | Promethean JVM Restart | Pruthvi Raj/Uddhav | Path: K:\BDTS-MW-Documents$\EIDIKOPITEAM\Handover\Noola Srinivas Handover\Automations\JVM Restart using Promethean File name: JVM restart document and start stop script.txt | completed & Implemented in UPI Portal, OBDX, CTS(Production) Subhasis bose & Team | Application team needs to implement in remaining applications If any application needs to implement this we need to share scritps and encrpted password. | Promethean, UCD
3 | Datasource password automation | Pruthvi Raj/Uddhav | Path: K:\BDTS-MW-Documents$\EIDIKOPITEAM\Handover\Noola Srinivas Handover\Automations\Datasource password automations File Name: Datasource Password Change Automation.docx | Scripts proided to RPA Team Amit khopade & Team | Pending with RPA Team, Currently RPA team is implementing on UAT UPI. | RPA
4 | Thread Dump Automation | Pruthvi Raj/Uddhav | K:\BDTS-MW-Documents$\EIDIKOPITEAM\Handover\Noola Srinivas Handover\Automations\Thread dump automation | Scripts proided to UCD Team Subhasis bose & Team | Pending with UCD Team | Promethean & UCD
5 | JVM Log collection during issue time | Pruthvi Raj/Uddhav | K:\BDTS-MW-Documents$\EIDIKOPITEAM\Handover\Noola Srinivas Handover\Automations\Log collection during issue time | Scripts proided to UCD Team Subhasis bose & Team | Pending with UCD Team | Promethean & UCD
6 | Log Purging For Linux | Pruthvi Raj/Uddhav | K:\BDTS-MW-Documents$\EIDIKOPITEAM\Handover\Noola Srinivas Handover\Automations\Log purging\linux | Scripts proided to UCD Team Subhasis bose & Team Last mile application we have implemented on UAT and signoff receieved | Pending with UCD Team/Application team | Promethean & UCD
7 | Log Purging For Solaris | Pruthvi Raj/Uddhav | K:\BDTS-MW-Documents$\EIDIKOPITEAM\Handover\Noola Srinivas Handover\Automations\Log purging\Solaris Document: K:\BDTS-MW-Documents$\EIDIKOPITEAM\Handover\Noola Srinivas Handover\Automations\Log purging\logpurging.docx | script is ready Tested in IGTB application it is working fine. We need to coordinate with application team for implementaion | NA | NA
8 | JVM health status | Pruthvi Raj/Uddhav | K:\BDTS-MW-Documents$\EIDIKOPITEAM\Handover\Noola Srinivas Handover\Automations\JVM Health status | Scripts proided to UCD Team | Pending with UCD Team/Application team | UCD & Promethean
r | JVM restart for DR Drill | Pruthvi Raj/Uddhav | K:\BDTS-MW-Documents$\EIDIKOPITEAM\Handover\Noola Srinivas Handover\Automations | As per application team request use these scripts for DR Drill activity | Curretly DR Automation team using this scripts. Few applications are SBA, ASBA, CTS | CP Tool
10 | POA Documents | Team | K:\BDTS-MW-Documents$\EIDIKOPITEAM\Handover\Noola Srinivas Handover\POA's | NA | NA | NA
11 | OBDX Schema password update | Pruthvi Raj/Uddhav | K:\BDTS-MW-Documents$\EIDIKOPITEAM\Handover\Noola Srinivas Handover\OBDX | It is different from regular DB password change activity we need to update the password in OPSS schema | NA | NA
12 | Batch JVM restart | Pruthvi Raj/Uddhav | K:\BDTS-MW-Documents$\EIDIKOPITEAM\Handover\Noola Srinivas Handover\Automations\Batch Stop Start | Scripts proided to Sudipto Team Contact person: Mayur sabane Tested in Batch production. | Sudipto Team | Control-M
13 | Domain Upgrade | Team | K:\BDTS-MW-Documents$\EIDIKOPITEAM\Handover\Noola Srinivas Handover\weblogic\Domain Upgrade | Knowledge Transfer | NA | NA